08. Governance & Delivery

ANTIER Project Assignment | Baseline: 13 September 2026 | Drafted from supplied working content

# 08. GOVERNANCE & DELIVERY

# 1. Project Management Plan (Summary)

Project Name: DMS Operational Transformation (Hypothetical)

Project Lead: Senior PM – AI & Client Delivery (Candidate)

Sponsor: COO, DMS Manufacturing

Duration: 32 weeks (Phase 0 to Phase 2); Phase 3+ as roadmap

Delivery Approach:

Phased, iterative delivery with clear gates between phases.

MVP-first to validate value and data readiness.

Governance cadence: Weekly core team, bi-weekly steering, monthly executive review.

Workstreams:

Business Analysis & Requirements (Owner: BA Lead)

Solution Design & Integration (Owner: Solution Architect – specialist)

Data & Information (Owner: Data Lead – specialist)

Change Management & Training (Owner: Change Manager)

Governance & Reporting (Owner: Project Lead)

Key Milestones:

M1: Phase 0 Discovery Complete (Week 4)

M2: MVP Go-Live (Week 16)

M3: Phase 2 Scale Complete (Week 32)

M4: Phase 3 Predictive Gate Review (Week 33+)

---

# 2. Work Breakdown Structure (WBS)

Level 1: DMS Operational Transformation

Level 2: Phase 0 – Discovery & Validation (Weeks 1–4)

L3: Workshops, Data Audit, MVP Scope Confirmation

Level 2: Phase 1 – MVP (Visibility) (Weeks 5–16)

L3: Build Forms, Deploy Dashboards, Train Users, Go-Live

Level 2: Phase 2 – Scale & Support (Weeks 17–32)

L3: Expand to All Lines, Add RAG, Enable Exports

Level 2: Phase 3 – Predictive Intelligence (Weeks 33+)

L3: Anomaly Detection Pilot, Alert Workflow, Outcome Tracking

---

# 3. Project Schedule (High-Level Timeline)

| PhaseStartEndDurationKey Deliverables |  |  |  |  |
| --- | --- | --- | --- | --- |
| Phase 0 | Week 1 | Week 4 | 4 weeks | Discovery Report, Data Readiness Baseline, MVP Scope |
| Phase 1 | Week 5 | Week 16 | 12 weeks | MVP Go-Live (1–2 lines), Training, KPI Baselines |
| Phase 2 | Week 17 | Week 32 | 16 weeks | Factory-Wide Rollout, RAG Assistant, Dashboards |
| Phase 3 | Week 33 | Week 48+ | 16+ weeks | Anomaly Detection Pilot, Alert Workflow, Optimization |

Dependencies:

Phase 1 start requires Phase 0 sign-off.

Phase 3 start requires data-readiness gate approval (KPI-01 ≥ 90%, 3+ months data).

---

# 4. Milestone Plan

| Milestone IDMilestone NamePlanned DateSuccess CriteriaOwner |  |  |  |  |
| --- | --- | --- | --- | --- |
| M1 | Phase 0 Discovery Complete | Week 4 | Discovery report approved; MVP scope signed off | Project Lead |
| M2 | MVP Go-Live | Week 16 | 80% user adoption; KPI-01 baseline captured | Project Lead |
| M3 | Phase 2 Scale Complete | Week 32 | All lines live; RAG assistant deployed | Project Lead |
| M4 | Phase 3 Gate Review | Week 33 | Data readiness validated; anomaly pilot approved | COO + Project Lead |

---

# 5. RACI Matrix

| Activity / DeliverableCOO (Sponsor)Plant ManagerMaintenance LeadIT ManagerProject Lead (Candidate)Solution Architect (Specialist) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Discovery Workshops | C | R | R | C | A | I |
| Requirements Sign-Off | C | A | R | R | A | I |
| Solution Design Review | I | C | C | R | A | R |
| MVP Go-Live Approval | A | R | R | C | A | I |
| Data Readiness Gate | C | R | R | A | A | R |
| Phase 3 Predictive Pilot | A | R | R | C | A | R |
| Monthly Steering Review | R | R | I | I | A | I |

Legend: R = Responsible, A = Accountable, C = Consulted, I = Informed

---

# 6. Risk Register

| Risk IDRisk DescriptionProbabilityImpactMitigation StrategyOwner |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| RISK-01 | Data quality insufficient for predictive AI | High | High | Phase 1 focuses on visibility; predictive deferred to Phase 3 | Project Lead |
| RISK-02 | User adoption low (frontline resistance) | Medium | High | Change champions; co-design workshops; quick wins in MVP | Change Manager |
| RISK-03 | CMMS integration delayed | Medium | Medium | Manual entry fallback; CSV import option | IT Manager |
| RISK-04 | Scope creep (requests for advanced features early) | Medium | Medium | Strict MVP scope; change control board | Project Lead |
| RISK-05 | Anomaly detection models underperform | Medium | Medium | Human-in-the-loop approval; model retraining feedback loop | Data Lead |
| RISK-06 | IT security policies block deployment | Low | High | Early IT engagement; SSO/RBAC alignment in Phase 1 | IT Manager |

---

# 7. Assumptions & Dependencies (Consolidated)

Assumptions (Reiterated from 01. Project Initiation):

A01: Historical data fragmented (requires new capture).

A02: No MES (or inaccessible).

A03: 4–6 roll-forming lines (sizing placeholder).

A04: Staff open to digital tools (requires change management).

A05: Basic network connectivity exists.

Dependencies:

D01: CMMS data export availability (for historical import).

D02: IT security policy alignment (for SSO/RBAC).

D03: Maintenance lead availability for workshops and UAT.

D04: COO sponsorship for monthly steering reviews.

---

# 8. Implementation Approach

Phased Rollout Strategy:

Pilot (MVP): 1–2 production lines; validate workflows, data capture, adoption.

Scale: Expand to all lines; add RAG, dashboards, exports.

Optimize: Deploy anomaly detection (if data ready); refine alerts.

Change Management:

Change Champions: Identify super-users in each shift.

Training: Role-based sessions (operators, maintenance, supervisors).

Adoption Metrics: Track login frequency, form completion rates, dashboard usage.

UAT Approach:

MVP UAT: Maintenance Lead + Shift Supervisors test forms, dashboards, audit logs.

Phase 2 UAT: Add RAG search, export functions.

Phase 3 UAT: Alert approval workflow, anomaly notifications.

Go-Live Criteria (MVP):

80% target users trained.

KPI-01 baseline captured.

Zero critical bugs in forms/dashboards.

COO sign-off on Phase 1 completion.

---

# 9. Phased Roadmap (Visual Summary)

text

Phase 0 (4w): Discovery -> MVP Scope -> Data Baseline   Phase 1 (12w): Forms + Dashboards + Taxonomy -> Go-Live (1–2 lines)   Phase 2 (16w): All Lines + RAG + Exports -> Factory-Wide Visibility   Phase 3 (16w+): Anomaly Detection + Alerts -> Predictive Maintenance

---

# 10. Governance Model

Governance Cadence:

Daily: Core team stand-up (Project Lead, BA, Change Manager).

Weekly: Workstream leads sync (Solution Architect, Data Lead, IT).

Bi-Weekly: Steering Committee (COO, Plant Manager, Project Lead).

Monthly: Executive Review (COO, IT Director, Project Lead).

Decision Gates:

Gate 1: Phase 0 -> Phase 1 (MVP scope approval).

Gate 2: Phase 1 -> Phase 2 (MVP success review).

Gate 3: Phase 2 -> Phase 3 (Data readiness validation).

Escalation Path:

Workstream Issue -> Project Lead -> Steering Committee -> COO (if blocked).

Reporting:

Weekly status report (RAG status, milestones, risks).

Monthly KPI dashboard (KPI-01 to KPI-07).

---